## Worksheet
Process Documentation - Gantt Chart Template
Task ID | Task Description | Start Date | End Date | Duration (Days) | Responsible Team/Person | Status
1 | Requirement Gathering | 2025-04-05 | 2025-04-12 | 8 | Business Analysts Team
2 | System Design Phase | 2025-04-13 | 2025-04-19 | 7 | Architecture Team
3 | Development (Frontend) | 2025-04-20 | 2025-05-16 | 28 | Frontend Developers
4 | Development (Backend) | 2025-04-20 | 2025-05-16 | 28 | Backend Developers
5 | Testing & QA | 2025-05-17 | 2025-06-14 | 29 | QA Team
6 | User Acceptance Testing (UAT) | 2025-06-15 | 2025-06-30 | 16 | End Users & Stakeholders
7 | Deployment & Go-Live | 2025-07-01 | 2025-07-03 | 3 | DevOps Team
8 | Post-Implementation Review | 2025-07-04 | 2025-07-11 | 8 | Mgmt & PMO Team
Total Duration: |  |  |  | 115 days
Template Version: 1.1 ¦ Purpose: Process Documentation ¦ Style/Version: Gantt Chart Template