## Worksheet
Process Documentation - Gantt Chart (Tracking View)
Task Name | Start Date | End Date | Duration (Days) | Progress | Dependencies
Project Initiation | Jan 05, 2024 | Jan 10, 2024 | 6 |  | N/A
Requirements Gathering | Jan 11, 2024 | Jan 25, 2024 | 15 |  | Project Initiation
System Design Phase | Jan 26, 2024 | Feb 10, 2024 | 16 |  | Requirements Gathering
Development Sprint 1 | Feb 11, 2024 | Feb 25, 2024 | 15 |  | System Design Phase
Development Sprint 2 | Feb 26, 2024 | Mar 10, 2024 | 13 |  | Development Sprint 1
Testing & QA Phase | Mar 11, 2024 | Mar 25, 2024 | 15 |  | Development Sprint 2
User Training & Documentation | Mar 26, 2024 | Apr 05, 2024 | 11 |  | Testing & QA Phase
Go-Live & Deployment | Apr 06, 2024 | Apr 10, 2024 | 5 |  | User Training & Documentation
Project Completion | Apr 10, 2024 | Apr 10, 2024 | 1 |  | Go-Live & Deployment
Note:This Gantt Chart represents the tracking view of the process documentation. Progress percentages are updated as milestones are achieved.