## Worksheet
Process Documentation - Weekly Gantt Chart (Weekly View)
Task ID | Task Name | Start Date | End Date | Status | Week of Jan 1, 2024 | Jan 8, 2024 | Jan 15, 2024 | Jan 22, 2024 | Jan 29, 2024
TASK001 | Project Initiation | Jan 1, 2024 | Jan 7, 2024 | In Progress | █ | █
TASK002 | Requirements Gathering | Jan 8, 2024 | Jan 14, 2024 | In Progress |  | █ | █
TASK003 | Design Phase | Jan 15, 2024 | Jan 21, 2024 | Not Started |  |  | █ | █
TASK004 | Development Implementation | Jan 22, 2024 | Jan 28, 2024 | Not Started |  |  |  | █ | █
TASK005 | Testing & Validation | Jan 29, 2024 | Feb 4, 2024 | Not Started |  |  |  | █ | █
MS001 | Project Kickoff Meeting | Jan 1, 2024 | Jan 1, 2024 | Milestone | ●
MS002 | Design Approval | Jan 15, 2024 | Jan 15, 2024 | Milestone |  |  | ●
Legend:█ = Active Task ¦ ● = Milestone