## Worksheet
Process Documentation - Freelancer Template
Process Step | Description | Responsible Party | Status & Timeline
1. Requirement Gathering | Capture client needs, objectives, and expectations through interviews and documentation. | Project Manager / Freelancer | In Progress - Due: 2025-04-15
2. Planning & Scheduling | Define project scope, milestones, deliverables, and timeline using Gantt charts. | Project Manager | Pending - Due: 2025-04-18
3. Design & Prototyping | Create wireframes, mockups, and interactive prototypes for client approval. | UI/UX Designer / Freelancer | Pending - Due: 2025-04-25
4. Development & Implementation | Build the solution based on approved designs and technical specifications. | Developers / Freelancer Team | Pending - Due: 2025-05-10
5. Testing & Quality Assurance | Conduct unit, integration, and user acceptance testing to ensure functionality. | QA Specialist / Freelancer | Pending - Due: 2025-05-18
6. Deployment & Go-Live | Launch the final product to production environment with monitoring. | DevOps Engineer / Freelancer | Pending - Due: 2025-05-25
7. Post-Launch Review & Support | Collect feedback, perform performance review, and provide initial support. | All Team Members / Freelancer | Pending - Due: 2025-06-10