## Monthly Planner - Client View
Monthly Planner - Client View
Process Documentation ¦ Monthly Overview
Week | Task Description | Owner | Start Date | End Date | Status
Week 1 | Project Kickoff Meeting & Requirements Gathering | John Smith (Project Lead) | 2024-04-01 | 2024-04-05 | In Progress
Week 1 | Initial Design Phase - Wireframes & Mockups | Sarah Johnson (UX Designer) | 2024-04-03 | 2024-04-15 | Pending
Week 1 | Client Feedback Collection & Review Session | Mike Chen (Client Liaison) | 2024-04-08 | 2024-04-15 | Pending
Week 2 | UI/UX Finalization & Approval Process | Sarah Johnson (UX Designer) | 2024-04-16 | 2024-04-30 | Pending
Week 3 | Frontend Development - Core Features Implementation | Lisa Park (Frontend Dev) | 2024-05-01 | 2024-05-15 | Pending
Week 3 | Data Model Design & Database Setup | David Lee (Backend Dev) | 2024-05-01 | 2024-05-15 | Pending
Week 4 | Integration Testing & Bug Fixing | Amy Wang (QA Lead) | 2024-05-16 | 2024-05-31 | Pending
Week 4 | User Acceptance Testing (UAT) & Feedback Loop | Mike Chen (Client Liaison) | 2024-05-23 | 2024-05-31 | Pending
Total Tasks Completed: |  |  |  |  | 0/12