## Monthly Planner - Manager View
Monthly Planner - Manager View
Week | Task / Objective | Owner | Status | Scheduled Date | Actual Progress (%) | Milestones / Deliverables
Week 1: January 1 - January 7, 2024
Week 1 | Project Kickoff Meeting & Goal Alignment | John Smith | High | Jan 2, 2024 | 100% | Meeting Minutes, Scope Document Approved
Week 1 | Resource Allocation & Team Assignment Review | Amanda Lee | Medium | Jan 3, 2024 | 75% | Roster Finalized, Budget Allocated
Week 2: January 8 - January 14, 2024
Week 2 | Develop Detailed Project Plan & Timeline | Michael Brown | Low | Jan 10, 2024 | 30% | Gantt Chart Draft Completed, Dependencies Mapped
Week 3: January 15 - January 21, 2024
Week 3 | Begin Development Phase (Phase A) | Sarah Johnson | Medium | Jan 16, 2024 | 55% | Core Modules Implemented, Testing Phase Initiated
Week 4: January 22 - January 31, 2024
Week 4 | Finalize Documentation & Prepare for UAT | David Kim | Low | Jan 25, 2024 | 40% | User Guides Drafted, Test Cases Written
Monthly Summary - January 1 - January 31, 2024
Overall Progress: | [5 empty] | 58%