## Monthly Planner - Summary View
Week | Tasks & Activities | [6 empty] | Total Hours
| Mon | Tue | Wed | Thu | Fri | Sat | Sun
Week 1 (01-07) | Review Process Docs 2h | Update SOPs 3h | Data Validation 2h | Clean-up Tasks 1.5h | Mtg: Team Planning 2.5h | - | - | 11h
Week 2 (08-14) | System Audit Prep 3h | Risk Assessment 2h | Status Report Draft 2.5h | Mtg: QA Review 3h | Draft Workflow Map 4h | - | - | 14.5h
Week 3 (15-21) | Clean-up & Optimization 3h | New Process Design 4h | User Feedback Integration 2.5h | Data Migration Planning 3.5h | Mtg: Cross-Team Alignment 2.5h | - | - | 16h
Week 4 (22-30) | Final Review & Approval 4h | Pilot Run Setup 3h | Pilot Execution 5h | Mtg: Post-Mortem & Feedback 3h | Closure Documentation 2.5h | -
Total Monthly Hours | 61.5 hours
Notes:
All hours are estimated and subject to change based on project progress.
Task status updates should be recorded weekly in the corresponding cell.
This summary is for internal process documentation and review purposes only.