## Worksheet
Order Tracker - Detailed Process Documentation
Order Information
Order ID | ORD-2023-XXXXX | Customer Name | John Doe | Date Placed | 2023-10-15 | Priority Level | High | Status | In Production
Product Details
Product Name | Premium Widget Model X | SKU | PWX-987654 | Quantity | 250 units | Unit Price ($) | 129.99 | Total Amount ($) | 32,497.50
Shipping & Delivery Information
Shipping Method | Express (2-day) | Tracking Number | TRK-789456123000 | Estimated Delivery Date | 2023-10-19 | Carrier | FedEx Express | Delivery Address | 123 Main Street Cityville, ST 54321 United States
Process Timeline & Milestones
Milestone | Planned Date | Actual Date | Status | Responsible Team/Person
Order Received & Verified | 2023-10-15 | 2023-10-15 | Completed | Order Processing Team
Production Initiated | 2023-10-16 | 2023-10-16 | Completed | Manufacturing Department
In Production (50%) | 2023-10-17 | 2023-10-17 | Completed | Manufacturing Department
In Production (85%) | 2023-10-18 | 2023-10-18 | Completed | Manufacturing Department
Quality Control Check | 2023-10-19 | 2023-10-19 | In Progress | QC Department
Shipping Preparation | 2023-10-20 |  | Pending | Logistics Team
Shipped | 2023-10-21 |  | Pending | Logistics Team
Delivered to Customer | 2023-10-23 |  | Pending | Delivery Service
Additional Notes & Remarks
Special Requirements: This order includes custom packaging with company branding. All units must be inspected for scratch marks prior to shipment. Communication Log: Customer requested expedited delivery on 2023-10-16. Status updated via email confirmation. Issue Raised: One unit was damaged during initial production run; replaced on 2023-10-17. No further defects reported.