## Worksheet
Process Documentation - Freelancer Planner Template
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Milestones & Notes(Progress Updates)
TASK-001 | Initial Project Discovery & Requirements Gathering | John Doe | 2024-03-25 | 2024-03-31 | In Progress | Client meeting scheduled. Initial scope defined.(Updated: 2024-03-26)
TASK-002 | Design Wireframes & User Flow Diagrams | Jane Smith | 2024-03-31 | 2024-04-15 | Pending | To be started after client approval of scope.(Next update: 2024-03-31)
TASK-003 | Frontend Development (UI Implementation) | Alex Johnson | 2024-04-16 | 2024-05-15 | Pending | Requires finalized design assets.(Next update: 2024-04-16)
TASK-004 | Backend API Integration & Database Setup | Lisa Wang | 2024-04-16 | 2024-05-31 | Pending | API specifications to be reviewed.(Next update: 2024-04-16)
TASK-005 | Testing & QA Verification (Beta Release) | Mike Chen | 2024-06-01 | 2024-06-15 | Pending | To be initiated after development completion.(Next update: 2024-06-01)
TASK-006 | Client Feedback Review & Final Revisions | John Doe | 2024-06-16 | 2024-06-30 | Pending | Final handover preparation.(Next update: 2024-06-16)
TASK-007 | Project Handover & Documentation Finalization | Jane Smith | 2024-07-01 | 2024-07-15 | Pending | Final documentation package to be delivered.(Next update: 2024-07-01)
TASK-008 | Post-Launch Review & Success Metrics Report | Mike Chen | 2024-07-16 | 2024-07-31 | Pending | Evaluate KPIs and client satisfaction.(Next update: 2024-07-16)
Legend: