## Worksheet
Quarterly Process Documentation Planner
Process Name | Responsible Team/Person | Q1 Goals & Objectives | Q2 Goals & Objectives | Q3 Goals & Objectives | Q4 Goals & Objectives
Process Category: Operations
Inventory Management System Update | Logistics Team - Jane Doe | Implement new tracking module by March 31 Status: In Progress • Due Date: Mar 28 | Test system with live data in April Status: Not Started • Due Date: Apr 15 | Roll out to all branches by July 31 Status: Not Started • Due Date: Jul 25 | Review performance and collect feedback by December 15 Status: Not Started • Due Date: Dec 10
Customer Onboarding Workflow | Customer Success - John Smith | Map current onboarding steps and identify bottlenecks by March 14 Status: Completed • Due Date: Mar 14 | Redesign workflow based on feedback by June 30 Status: In Progress • Due Date: Jun 28 | Implement revised process in July and train team Status: Not Started • Due Date: Jul 15 | Monitor KPIs for three months post-launch Status: Not Started • Due Date: Dec 15
Process Category: HR & Onboarding
New Hire Orientation Program | HR Department - Lisa Chen | Develop new orientation materials by March 31 Status: In Progress • Due Date: Mar 25 | Pilot program with Q2 hires in April Status: Not Started • Due Date: Apr 10 | Refine based on feedback by September 30 Status: Not Started • Due Date: Sep 25 | Standardize across all departments by December 15 Status: Not Started • Due Date: Dec 10
Performance Review Cycle | HR Leadership - Michael Brown | Update evaluation framework by March 31 Status: Completed • Due Date: Mar 28 | Pilot new review forms in Q2 Status: In Progress • Due Date: Jun 15 | Collect feedback and finalize system by September 30 Status: Not Started • Due Date: Sep 25 | Launch enterprise-wide in October with training Status: Not Started • Due Date: Oct 15
Quarterly Summary & Key Metrics
Total Processes Documented | 4 | 100% | 85% | 60% | 25%
Updated as of January 10, 2024 • Last Reviewed: January 5, 2024