## Worksheet
Advanced Project Plan – Process Documentation
Phase | Task Name | Description | Owner | Start Date | End Date | Status
Initiation | Define Project Scope | Identify objectives, deliverables, and constraints. | Jane Smith | 2024-01-15 | 2024-01-31 | Completed
Initiation | Stakeholder Analysis | Map all key stakeholders and their expectations. | Mike Johnson | 2024-01-16 | 2024-01-31 | Completed
Planning | Develop Work Breakdown Structure (WBS) | Break down project deliverables into manageable tasks. | Amy Lee | 2024-02-01 | 2024-02-15 | In Progress
Planning | Create Detailed Schedule & Milestones | Assign timelines and dependencies using Gantt chart. | Robert Chen | 2024-02-05 | 2024-03-15 | Pending
Execution | Resource Allocation & Team Onboarding | Assign team members and provide onboarding materials. | Sarah Wilson | 2024-03-18 | 2024-03-31 | Pending
Execution | Begin Development Phase | Start coding, design, and prototyping. | Daniel Brown | 2024-04-01 | 2024-06-30 | Pending
Monitoring & Control | Weekly Status Reviews & Reporting | Track progress, risks, and adjustments. | Jane Smith | 2024-04-15 | Ongoing | Pending
Closure | Final Testing & QA Sign-off | Conduct final user acceptance testing and approvals. | Grace Patel | 2024-07-01 | 2024-07-31 | Pending
Closure | Project Handover & Documentation Finalization | Deliver final documents and knowledge transfer. | Liam Garcia | 2024-08-01 | 2024-08-15 | Pending
Closure | Post-Implementation Review | Evaluate performance and lessons learned. | Emily Clark | 2024-08-16 | 2024-08-31 | Pending
Total Tasks: | [5 empty] | 10
Completed: | [5 empty] | 2
In Progress: | [5 empty] | 1
Pending: | [5 empty] | 7