## Worksheet
PROCESS DOCUMENTATION - PROJECT PLAN (ANALYSIS VIEW)
Phase | Task | Owner | Status | Start Date | End Date | Description / Notes
Initiation | Define Project Scope and Objectives | Project Manager | To Do | 2023-10-01 | 2023-10-15 | Gather requirements from stakeholders.
Initiation | Identify Key Stakeholders | Project Coordinator | In Progress | 2023-10-05 | 2023-10-18 | Create stakeholder mapping matrix.
Analysis | Conduct Requirement Gathering Workshop | Business Analyst | Completed | 2023-10-15 | 2023-10-25 | Sessions conducted with 8 key departments.
Analysis | Define System Requirements | Systems Analyst | In Progress | 2023-10-20 | 2023-11-10 | Draft detailed functional and non-functional specs.
Design | Create System Architecture Diagrams | Lead Architect | To Do | 2023-11-05 | 2023-11-20 | Include cloud integration components.
Design | Develop UI/UX Wireframes | UI Designer | To Do | 2023-11-15 | 2023-12-05 | Figma prototypes to be reviewed by UX team.
Development | Set Up Development Environment | DevOps Engineer | In Progress | 2023-11-10 | 2023-11-25 | Docker and CI/CD pipeline configuration.
Development | Implement Core Modules | Senior Developer | To Do | 2023-11-25 | 2024-01-15 | First iteration of backend services.
Testing | Write Test Cases and Scenarios | QA Lead | In Progress | 2023-12-01 | 2023-12-15 | Basis for regression and integration testing.
Testing | Execute System Integration Test (SIT) | QA Team | To Do | 2024-01-16 | 2024-01-31 | Cover end-to-end workflow validation.
Deployment | Prepare Production Readiness Checklist | Release Manager | To Do | 2024-01-30 | 2024-02-15 | Involves security and compliance review.
Deployment | Deploy to Production Environment | DevOps Team | To Do | 2024-02-16 | 2024-02-18 | Scheduled during maintenance window.
Project Summary
Total Duration: |  | 2023-10-01 to 2024-02-18
Current Status: |  | In Progress (Phase: Analysis & Design)
This document is an internal project plan template. Version 1.0 ¦ Created on 2023-10-01