## Worksheet
ANNUAL PROJECT PLAN - PROCESS DOCUMENTATION
Phase / Task | Start Date | End Date | Responsible Party | Status | Budget (USD) | Milestone Achieved(Y/N) | Notes / Comments
Project Initiation & Planning | 01-Jan-2024 | 15-Feb-2024 | Project Manager | In Progress | $15,000 | N | Initial stakeholder meetings scheduled.
Q1 - January to March 2024
Process Mapping & Analysis | 01-Feb-2024 | 31-Mar-2024 | Process Analysts | To Do | $8,500 | N | Data collection in progress.
Q2 - April to June 2024
Documentation Development | 01-Apr-2024 | 31-May-2024 | Technical Writers | To Do | $12,000 | N | Draft templates created.
Q3 - July to September 2024
Review & Feedback Integration | 01-Jul-2024 | 30-Sep-2024 | Stakeholders & Review Board | To Do | $5,000 | N | Feedback cycle scheduled.
Q4 - October to December 2024
Finalization & Approval | 01-Oct-2024 | 31-Dec-2024 | Project Lead & Management | To Do | $7,500 | N | Final sign-off process.
Total Project Overview
Total Duration | 01-Jan-2024 to 31-Dec-2024 |  | $48,000
Prepared by: John Doe ¦ Date: 31-Dec-2023 ¦ Version: 1.1 ¦ Approved by: Jane Smith