## Project Plan - Client View
Phase/Task | Start Date | End Date | Status | Owner | Description
Project Initiation | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith | Define project scope and objectives.
Requirements Gathering | 2023-10-06 | 2023-10-15 | Pending | John Doe | Capture functional and non-functional requirements.
Design Phase | 2023-10-16 | 2023-10-30 | Not Started | Alice Johnson | Create system architecture and UI mockups.
Development | 2023-10-31 | 2023-12-15 | Not Started | Mike Brown | Code implementation and unit testing.
Testing & QA | 2023-12-16 | 2024-01-15 | Not Started | Sarah Wilson | Conduct integration, system, and user acceptance testing.
Deployment | 2024-01-16 | 2024-01-31 | Not Started | Lisa Taylor | Publish to production environment and monitor.
Post-Launch Review | 2024-02-01 | 2024-02-15 | Not Started | Jane Smith | Evaluate project outcomes and gather feedback.
Notes:
Status options: Not Started, In Progress, Pending, Completed.
All dates are subject to change based on project milestones.
Regular review meetings scheduled every Monday at 10:00 AM.