## Project Plan Dashboard View
Project Plan Dashboard View
Phase / Task | Owner | Start Date | End Date | Status | Progress (%)
Phase 1: Requirements Gathering | Jane Smith | 2023-09-01 | 2023-09-15 | In Progress | 75%
Phase 2: Design & Architecture | Mike Johnson | 2023-09-16 | 2023-10-05 | In Progress | 45%
Phase 3: Development | Taylor Lee | 2023-10-06 | 2023-11-15 | Delayed (Issues Identified) | 20%
Phase 4: Testing | Alex Rivera | 2023-11-16 | 2023-12-05 | Not Started | 0%
Phase 5: Deployment | Sophia Clark | 2023-12-06 | 2023-12-15 | Not Started | 0%
Phase 6: Documentation & Training | David Kim | 2023-12-16 | 2024-01-15 | Not Started | 0%
Total Project Progress |  |  |  | In Progress (Avg: 35%) | 35%
Legend: