## Worksheet
Process Documentation
Template Type: Project Plan ¦ Style/Version: Data Version
Task ID | Task Name | Description | Responsible Party | Start Date | End Date | Status
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | Project Manager | 2024-04-01 | 2024-04-15 | In Progress
T002 | Requirements Gathering | Capture detailed functional and non-functional requirements. | Business Analyst | 2024-04-16 | 2024-05-15 | Not Started
T003 | Design Phase | Create system architecture and UI/UX designs. | Lead Designer, Architect | 2024-05-16 | 2024-06-30 | Not Started
T004 | Development Phase | Implement system modules based on design specifications. | Development Team | 2024-07-01 | 2024-10-31 | Not Started
T005 | Testing & QA | Conduct unit, integration, and user acceptance testing. | QA Team | 2024-11-01 | 2024-11-30 | Not Started
T006 | Deployment & Go-Live | Deploy system to production environment and support rollout. | DevOps Team, Project Manager | 2024-12-01 | 2024-12-15 | Not Started
T007 | Post-Launch Review | Evaluate project success and document lessons learned. | Project Manager, Stakeholders | 2024-12-16 | 2024-12-31 | Not Started