## Worksheet
Task ID | Task Name | Description | Responsible Person | Start Date | End Date | Status
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | Jane Smith | 2023-10-01 | 2023-10-05 | Completed
T002 | Requirements Gathering | Collaborate with stakeholders to gather detailed requirements. | Mike Johnson | 2023-10-06 | 2023-10-15 | In Progress
T003 | Design Phase | Create system architecture and UI/UX designs. | Sarah Lee | <2023-10-16 | 2023-10-31 | Pending
T004 | Development Phase | Implement system features based on design documents. | David Brown | 2023-11-01 | 2023-12-15 | Pending
T005 | Testing Phase | Conduct unit, integration, and system testing. | Lisa White | 2023-12-16 | 2024-01-15 | Pending
T006 | User Acceptance Testing (UAT) | Client-side testing for final approval. | Robert Green | 2024-01-16 | 2024-01-31 | Pending
T007 | Deployment Phase | Deploy system to production environment. | Amanda Taylor | 2024-02-01 | 2024-02-15 | Pending
T008 | Post-Deployment Review | Conduct review meeting and document lessons learned. | Jane Smith | 2024-02-16 | 2024-03-31 | Pending