## Employee View - Project Plan
Employee Name | Role | Task Description | Start Date | Due Date | Status | Brief Notes / Comments
Project Kickoff & Planning Phase
John Smith | Project Manager | Define project scope and objectives | 2024-01-05 | 2024-01-15 | In Progress | Initial requirements gathered from stakeholders.
Alice Johnson | Lead Developer | Setup development environment and tools | 2024-01-05 | 2024-01-10 | Completed | All tools installed and tested successfully.
Robert Lee | UX Designer | Create wireframes for main application screens | 2024-01-10 | 2024-01-25 | Pending | Waiting on initial requirement sign-off.
Development & Implementation Phase
Maria Garcia | Frontend Developer | Implement login and dashboard UI components | 2024-01-15 | 2024-02-15 | In Progress | 65% complete; testing phase next week.
Daniel Kim | Backend Developer | Develop API endpoints for user management | 2024-01-20 | 2024-02-10 | In Progress | API v1.1 complete, awaiting security review.
Sophia Brown | QA Engineer | Create test cases for user authentication module | 2024-01-18 | 2024-01-31 | Completed | All test scenarios documented and approved.
Testing & Deployment Phase
James Wilson | DevOps Engineer | Set up CI/CD pipeline for automated deployment | 2024-02-15 | 2024-03-15 | Pending | In progress on staging environment configuration.
Linda Taylor | Project Manager | Conduct user acceptance testing (UAT) | 2024-03-01 | 2024-03-31 | Pending | Scheduling sessions with end-users.
Total Tasks |  | 8 | Status Summary: 3 In Progress, 2 Completed, 3 Pending