## Financial View - Project Plan
FINANCIAL VIEW - PROJECT PLAN
Phase | Task | Start Date | End Date | Owner | Budget (USD) | Spend to Date (USD) | Budget Variance (USD) | Status
Initiation | Project Charter Approval | 2024-01-15 | 2024-01-31 | Jane Smith | 5,000.00 | 3,200.50 | 1,799.50 | On Track
Planning | Resource Allocation & Team Setup | 2024-02-01 | 2024-02-15 | John Doe | 8,500.00 | 6,857.33 | 1,642.67 | On Track
Execution | Design Phase - UI/UX Development | 2024-02-16 | 2024-03-31 | Alice Brown | 15,000.00 | 13,478.95 | 1,521.05 | On Track
Execution | Development Phase - Core Features Build | 2024-04-01 | 2024-06-30 | Robert Green | 55,000.00 | 38,791.42 | 16,208.58 | On Track
Execution | Testing & QA Cycle 1 | 2024-07-01 | 2024-07-31 | Sarah Wilson | 18,500.00 | 9,865.24 | 8,634.76 | On Track
Execution | Deployment Preparations & Training | 2024-08-01 | 2024-08-31 | Maria Lopez | 12,750.00 | 6,932.87 | 5,817.13 | On Track
Closeout | Final Review & Project Closure | 2024-09-01 | 2024-09-30 | Jane Smith | 6,500.00 | 3,124.65 | 3,375.35 | On Track
Total Budget: |  |  |  |  | 120,250.00 | 81,346.96 | 38,903.04 | Overall: On Track