## Project Plan - Freelancer Style
Project Plan - Freelancer Style
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete | Notes/Comments
#P001 | Initial Project Kickoff & Requirements Gathering | Jane Doe (Client) | 2024-04-01 | 2024-04-05 | Complete | 100% | Requirements documented and approved.
#P002 | UI/UX Design & Wireframes | John Smith (Freelancer) | 2024-04-06 | 2024-04-15 | Complete | 100% | Final designs approved by client.
#P003 | Frontend Development (HTML/CSS/JS) | John Smith (Freelancer) | 2024-04-16 | 2024-05-10 | Pending | 75% | In progress; responsive layout under testing.
#P004 | Backend Integration & API Setup | Alex Johnson (Freelancer) | 2024-05-11 | 2024-06-15 | Pending | 35% | Database schema finalized. API endpoints in development.
#P005 | User Testing & Feedback Collection | Jane Doe (Client) | 2024-06-16 | 2024-07-15 | Delayed | 5% | Scheduled for review post-backend completion.
#P006 | Final Deployment & Go-Live | All Team Members | 2024-07-16 | 2024-07-31 | Pending | 0% | To be scheduled after final testing.
This project plan is a living document. Status updates are performed weekly.