## Worksheet
Project Plan - Process Documentation
Large Business Project Overview
Task ID | Activity / Milestone | Owner | Start Date | Due Date | Status | Progress (%) | Priority Level | Dependencies / Notes | Approval Status
PP-001 | Project Kickoff & Initiation | Jane Smith (PM) | 2024-04-05 | 2024-04-12 | Completed | 100% | High | Stakeholder alignment achieved. | Pending Review
PP-002 | Requirements Gathering & Validation | Mike Johnson (BA) | 2024-04-13 | 2024-05-17 | In Progress | 65% | High | Client workshop scheduled for April 28. | Pending Approval
PP-003 | System Design & Architecture Review | Sarah Chen (Lead Architect) | 2024-05-18 | 2024-06-15 | Delayed | 30% | High | Waiting for design sign-off from IT Security. | Pending Approval
PP-004 | Development Phase - Module A (Core Engine) | David Lee (Tech Lead) | 2024-06-16 | 2024-08-15 | In Progress | 55% | High | API integration underway. | Pending Approval
PP-005 | Data Migration Planning & Testing | Linda Wang (Data Engineer) | 2024-07-15 | 2024-09-30 | In Progress | 48% | Medium | Migrate legacy data in stages. | Pending Approval
PP-006 | User Acceptance Testing (UAT) | Alice Brown (QA Lead) | 2024-10-01 | 2024-11-30 | Delayed | 5% | High | UAT environment not ready. | Pending Approval
PP-007 | Final Deployment & Go-Live | Ryan Taylor (Ops Manager) | 2024-12-01 | 2024-12-31 | Not Started | 0% | High | Contingency plan in place. | Pending Approval
Total Project Progress: |  |  |  |  | Overall Status: | 58% |  |  | Pending Review