## Project Plan - Manager View
Project Plan - Manager View
Purpose:Process Documentation
ID | Task Name | Description | Owner | Start Date | End Date | Status | Priority
document.addEventListener("DOMContentLoaded", function () { const tableBody = document.getElementById('table-body'); // Sample task data const tasks = [ { id: "TASK001", name: "Define Project Scope", desc: "Outline project objectives and deliverables.", owner: "Jane Smith", start: "2023-10-01", end: "2023-10-05", status: "Completed", priority: "High" }, { id: "TASK002", name: "Create Process Flowcharts", desc: "Design visual representations of business processes.", owner: "Mark Johnson", start: "2023-10-06", end: "2023-10-15", status: "In Progress", priority: "High" }, { id: "TASK003", name: "Gather Requirements from Stakeholders", desc: "Collect input and feedback from key users.", owner: "Linda Brown", start: "2023-10-16", end: "2023-10-25", status: "Pending", priority: "Medium" }, { id: "TASK004", name: "Document All Processes", desc: "Write detailed process documentation for each workflow.", owner: "David Lee", start: "2023-10-26", end: "2023-11-15", status: "Pending", priority: "High" }, { id: "TASK005", name: "Review and Approve Documentation", desc: "Conduct internal review with project team and stakeholders.", owner: "Sarah Wilson", start: "2023-11-16", end: "2023-11-25", status: "Pending", priority: "Medium" }, { id: "TASK006", name: "Finalize & Distribute Process Manual", desc: "Compile and share the final version with all relevant departments.", owner: "James Taylor", start: "2023-11-26", end: "2023-12-05", status: "Pending", priority: "Low" } ]; tasks.forEach(task => { const row = document.createElement("tr"); row.innerHTML = ` <td>${task.id} <td>${task.name} <td>${task.desc} <td>${task.owner} <td>${task.start} <td>${task.end} <td><span class="status-${task.status.toLowerCase()}">${task.status} <td><strong>${task.priority}`; tableBody.appendChild(row); }); });© 2023 Project Management Office. All rights reserved.