## Worksheet
Monthly Project Plan - Process Documentation
Month | Task / Activity | Description | Responsible Party | Status | Start Date | End Date
January 2024 | Project Kickoff Meeting | Initiate the project with stakeholders, define objectives, and assign roles. | Project Manager | In Progress | 2024-01-05 | 2024-01-10
January 2024 | Process Mapping Workshop | Capture current workflows and identify bottlenecks. | Process Analysts | Pending | 2024-01-15 | 2024-01-20
February 2024 | Draft Process Documentation | Create initial documentation based on mapped processes. | Documentation Team | Pending | 2024-02-01 | 2024-02-15
February 2024 | Review & Feedback Session | Gather input from department leads on draft documentation. | Stakeholders | Pending | 2024-02-16 | 2024-02-23
March 2024 | Finalize Documentation & Publish | Update final version and deploy to internal knowledge base. | Document Manager | Pending | 2024-03-01 | 2024-03-15
March 2024 | Training Sessions | Conduct training for team members on new documented processes. | Trainer Team | Pending | 2024-03-18 | 2024-03-31
April 2024 | Process Review & Audit | Evaluate process adherence and identify improvement areas. | Quality Assurance Team | Pending | 2024-04-01 | 2024-04-15
April 2024 | Status Reporting & Closure | Submit final report and close project documentation. | Project Manager | Pending | 2024-04-16 | 2024-04-30
Monthly Summary & Key Metrics (to be updated monthly)
Tasks Completed This Month |  | [To be filled]
Bottlenecks / Risks |  | [To be filled]
Next Month's Focus |  | [To be filled]
This document is a monthly project plan template for process documentation. Update status, dates, and comments regularly to ensure effective tracking.