## Project Plan - Planning View
Project Plan - Planning View
Task ID | Task Name | Owner | Start Date | End Date | Status
Project Initiation Phase
P001 | Define Project Scope | Project Manager | 2023-10-01 | 2023-10-07 | In Progress
P002 | Identify Stakeholders | Project Manager | 2023-10-08 | 2023-10-14 | To Do
P003 | Develop Project Charter | Project Manager | 2023-10-15 | 2023-10-21 | To Do
Planning Phase
P004 | Define Requirements | Business Analyst | 2023-10-22 | 2023-11-05 | To Do
P005 | Develop Work Breakdown Structure (WBS) | Project Manager | 2023-11-06 | 2023-11-12 | To Do
P006 | Create Project Schedule (Gantt Chart) | Project Manager | 2023-11-13 | 2023-11-19 | To Do
P007 | Resource Planning & Allocation | HR Manager / Project Manager | 2023-11-20 | 2023-11-26 | To Do
Execution Phase
P008 | Begin Development Work | Development Team | 2023-11-27 | 2024-01-31 | To Do
P009 | Conduct Design Reviews | Lead Architect | 2023-12-01 | 2024-01-15 | To Do
P010 | Perform Quality Assurance Testing | QA Team | 2024-02-01 | 2024-03-15 | To Do
Closure Phase
P011 | Finalize Project Documentation | Project Manager | 2024-03-16 | 2024-03-31 | To Do
P012 | Conduct Project Review & Lessons Learned | Project Manager / Team Lead | 2024-04-01 | 2024-04-15 | To Do
P013 | Project Handover & Sign-off | Project Manager / Client Rep | 2024-04-16 | 2024-04-30 | To Do
Total Tasks: |  |  |  |  | 13