## Worksheet
Task ID | Task Name | Responsible Team/Person | Start Date | End Date | Status | Description
P1001 | Project Initiation & Planning | Project Manager | 2024-04-01 | 2024-04-15 | In Progress | Capture project scope, objectives, and stakeholders.
P1002 | Requirements Gathering | Business Analysts | 2024-04-16 | 2024-05-15 | To Do | Capture functional and non-functional requirements.
P1003 | Design Phase | UX/UI Designers, Architects | 2024-05-16 | 2024-06-15 | To Do | Create system architecture and wireframes.
P1004 | Development Sprint 1 | Development Team | 2024-06-16 | 2024-07-31 | To Do | Build core modules and foundational components.
P1005 | Development Sprint 2 | Development Team | 2024-08-01 | 2024-09-30 | To Do | Implement additional features and enhancements.
P1006 | Testing & QA Phase | QA Engineers, Testers | 2024-10-01 | 2024-11-30 | To Do | Execute test cases, bug fixing, and regression testing.
P1007 | User Training & Documentation | Training Coordinator, Technical Writers | 2024-12-01 | 2024-12-31 | To Do | Prepare user manuals and conduct training sessions.
P1008 | Deployment & Go-Live | IT Operations, DevOps Team | 2025-01-01 | 2025-01-31 | To Do | Deploy system to production and monitor initial performance.
P1009 | Post-Implementation Review | Project Manager, Stakeholders | 2025-02-01 | 2025-02-14 | To Do | Evaluate project success and document lessons learned.