## Worksheet
Quarterly Project Plan - Process Documentation
Q2 2024 ¦ Project ID: PRJ-Q2-2024-001
Phase/Task | Description | Responsible Party | Start Date | End Date | Status
Project Initiation & Planning | Define objectives, scope, deliverables, and stakeholders. | Project Manager | 2024-04-01 | 2024-04-15 | In Progress
Requirements Gathering | Capture functional and non-functional requirements. | Business Analysts | 2024-04-16 | 2024-05-15 | Pending
Process Design & Documentation | Create flowcharts, SOPs, and process maps. | Process Architects | 2024-05-16 | 2024-06-15 | Pending
System Development & Integration | Develop and integrate systems based on documented processes. | Development Team | 2024-06-16 | 2024-07-31 | Pending
User Acceptance Testing (UAT) | Validate processes and systems with end users. | QA Team & Stakeholders | 2024-08-01 | 2024-08-15 | Pending
Training & Knowledge Transfer | Conduct training sessions and documentation handover. | Training Coordinators | 2024-08-16 | 2024-08-31 | Pending
Go-Live & Monitoring | Deploy system and monitor performance for first month. | Operations Team | 2024-09-01 | 2024-09-30 | Pending
Total Duration (Est.) | Q2 2024 – Q3 2024 (10 weeks)