## Project Plan - Report Version
Project Plan - Report Version
Task ID | Task Name | Description | Responsible Team Member(s) | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | Jane Doe, John Smith | 2023-10-01 | 2023-10-05 | In Progress | 85%
T002 | Requirements Gathering | Capture and document business requirements. | Alice Johnson | 2023-10-06 | 2023-10-15 | To Do | 0%
T003 | System Design Phase | Create architectural and technical design documents. | Robert Brown, Emily Davis | 2023-10-16 | 2023-10-30 | To Do | 0%
T004 | Development Implementation | Develop system components according to design. | Team A (5 members) | 2023-10-31 | 2024-01-31 | To Do | 0%
T005 | Testing & QA | Perform unit, integration, and system testing. | Quality Assurance Team | 2024-02-01 | 2024-03-15 | To Do | 0%
T006 | User Training & Documentation | Prepare user manuals and conduct training sessions. | Training Coordinator, Documentation Lead | 2024-03-16 | 2024-03-31 | To Do | 0%
T007 | Go-Live & Deployment | Deploy system to production environment. | IT Operations Team, Project Manager | 2024-04-01 | 2024-04-15 | To Do | 0%
T008 | Post-Implementation Review | Evaluate project success and identify lessons learned. | Project Manager, Stakeholders | 2024-04-16 | 2024-05-31 | To Do | 0%
Report Version ¦ Generated on 2023-10-15 ¦ Project Plan for Internal Documentation