## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Status
T001 | Project Initiation | Project Manager | 2023-10-01 | 2023-10-05 | Completed
T002 | Requirements Gathering | Business Analyst | 2023-10-06 | 2023-10-15 | In Progress
T003 | System Design | Lead Developer | 2023-10-16 | 2023-10-25 | Not Started
T004 | Development Phase 1 | Development Team | 2023-10-26 | 2023-11-15 | Not Started
T005 | Testing & QA | QA Team | 2023-11-16 | 2023-11-30 | Not Started
T006 | Deployment Preparation | DevOps Engineer | 2023-12-01 | 2023-12-05 | Not Started
T007 | Final Deployment | Project Manager | 2023-12-06 | 2023-12-10 | Not Started
T008 | Closure & Review | Project Manager | 2023-12-11 | 2023-12-15 | Not Started