## Project Plan - Small Business
Phase | Task | Responsible Person | Start Date | End Date | Status
Phase 1: Planning
1.1 | Define Project Scope | John Doe | 2023-10-05 | 2023-10-10 | In Progress
1.2 | Identify Key Stakeholders | Jane Smith | 2023-10-11 | 2023-10-15 | Not Started
Phase 2: Design
2.1 | Create Project Workflow Diagram | Mike Johnson | 2023-10-16 | 2023-10-25 | Not Started
Phase 3: Development
3.1 | Build Core System Components | Amy Brown | 2023-10-26 | 2023-11-15 | Not Started
Phase 4: Testing
4.1 | Conduct Unit Testing | Tom Wilson | 2023-11-16 | 2023-11-25 | Not Started
Phase 5: Deployment
5.1 | Deploy to Production Environment | Sarah Lee | 2023-11-26 | 2023-11-30 | Not Started
Phase 6: Review
6.1 | Final Project Evaluation | John Doe | 2023-12-01 | 2023-12-05 | Not Started
Note:This Project Plan template is designed for small business use. Status updates should be reviewed weekly.
Created on: 2023-10-04 ¦ Version: 1.0