## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Milestone(Y/N)
P001 | Project Initiation & Kickoff | Alice Johnson (PM) | 2024-04-01 | 2024-04-15 | In Progress | Y
P002 | Market Research & Validation | Bob Smith (Research) | 2024-04-16 | 2024-05-15 | To Do
P003 | User Persona Development | Carol Lee (UX) | 2024-05-16 | 2024-06-15 | To Do
P004 | Prototype Design & Testing | David Kim (Design) | 2024-06-16 | 2024-07-31 | To Do
P005 | Development Sprint 1 (Core Features) | Eva Patel (Dev Lead) | 2024-08-01 | 2024-09-30 | To Do
P006 | User Testing & Feedback Loop | Frank Wilson (QA) | 2024-10-01 | 2024-11-30 | To Do
P007 | Final Development & Bug Fixing | Gina Moore (Dev) | 2024-12-01 | 2025-01-31 | To Do
P008 | Go-to-Market Launch Plan | Hank Brown (Marketing) | 2025-01-15 | 2025-02-14 | To Do
P009 | Product Launch & Campaign Activation | Iris Taylor (Marketing) | 2025-02-15 | 2025-03-31 | To Do
P010 | Post-Launch Review & Iteration Plan | James Reed (PM) | 2025-04-01 | 2025-04-30 | To Do