## Project Plan - Tracking View
Project Plan - Tracking View
Task ID | Task Name | Owner | Start Date | Due Date | Status | % Complete
TP001 | Project Initiation & Planning | Alice Johnson | 2024-01-05 | 2024-01-15 | High Risk | 95%
TP002 | Requirements Gathering | Bob Smith | 2024-01-16 | 2024-01-31 | On Track | 85%
TP003 | UI/UX Design Phase 1 | Claire Brown | 2024-02-01 | 2024-02-15 | On Track | 78%
TP004 | Backend Development Setup | Daniel Lee | 2024-02-16 | 2024-03-15 | On Track | 65%
TP005 | Frontend Development Sprint 1 | Elena Martinez | 2024-03-16 | 2024-03-31 | On Track | 55%
TP006 | System Integration Testing | Felix Garcia | 2024-04-01 | 2024-04-15 | On Track | 35%
TP007 | User Acceptance Testing (UAT) | Gina White | 2024-04-16 | 2024-04-25 | On Track | 15%
TP008 | Final Deployment & Go-Live | Hector King | 2024-04-26 | 2024-04-30 | On Track | 5%
Overall Project Completion: | [5 empty] | 71%