## Worksheet
Weekly Project Plan - Process Documentation
Week Starting | Activity/Task | Owner | Status | Progress (%) | Notes/Comments
01/01/2024 | Define project scope and objectives | Project Manager | In Progress | 75 | Final stakeholder review scheduled for Friday.
01/08/2024 | Conduct process discovery workshops | Lead Analyst | To Do | 0 | Meeting with department heads confirmed.
01/15/2024 | Create initial process flow diagrams | Process Designer | Not Started | 0 | Draft to be reviewed by team next week.
01/22/2024 | Review and validate documentation with stakeholders | Quality Lead | To Do | 0 | Stakeholder list finalized.
01/29/2024 | Implement feedback and finalize documentation | Documentation Team | To Do | 0 | Baseline version ready for review.
Total Progress: |  |  |  |  | 30%