## Worksheet
Step | Process Name | Description | Responsible Party | Status | Deadline
1 | Requirement Gathering | Capture detailed client requirements through interviews and workshops. | Project Manager, Business Analyst | In Progress | 2024-05-15
2 | Process Analysis & Mapping | Analyze current workflows and define future state processes. | Business Analyst, Process Consultant | Pending | 2024-05-20
3 | System Design & Prototyping | Create system architecture and interactive prototypes for client review. | UX Designer, Solution Architect | Not Started | 2024-05-25
4 | User Acceptance Testing (UAT) | Clients test the solution in real-world scenarios and provide feedback. | Client Representative, QA Team | Not Started | 2024-06-15
5 | Training & Documentation | Prepare training materials and conduct onboarding sessions. | Training Specialist, Documentation Lead | Not Started | 2024-06-20
6 | Go-Live & Support Handover | Deploy the solution and transition to live operations with support. | Project Manager, IT Support | Not Started | 2024-06-30
7 | Post-Launch Review | Evaluate project success and document lessons learned. | Project Manager, Client Stakeholders | Not Started | 2024-07-10