## Worksheet
Step ID | Process Step | Responsible Role | Input | Output | Duration (min) | Status
1 | Project Initiation | Project Manager | Business Request | Project Charter | 30 | Planned
2 | Requirements Gathering | Business Analyst | Project Charter | Functional Requirements Document | 90 | Not Started
3 | Design Phase | System Architect | Functional Requirements Document | System Design Specification | 120 | Not Started
4 | Development | Development Team | System Design Specification | Developed Code & Modules | 480 | Not Started
5 | Testing & QA | QA Team | Developed Code & Modules | Test Reports, Bug Fixes | 240 | Not Started
6 | Deployment | DevOps Engineer | Test Reports, Bug Fixes | Live Production System | 60 | Not Started
7 | Post-Implementation Review | Project Manager | Live Production System | Project Closure Report | 60 | Not Started