## Worksheet
Process Documentation
Template Type:Project Template
Process Step | Description | Status | Responsible Person | Dates (Start/End) | Notes/Comments
Project Initiation | Define project goals, scope, deliverables and stakeholder expectations. | Planned | John Doe | 2023-10-01 / 2023-10-05 | Client approval pending.
Data Collection & Analysis | Gather and analyze all necessary data for project requirements. | In Progress | Jane Smith | 2023-10-06 / 2023-10-15 | Initial datasets received.
Design Phase | Create wireframes, mockups, and design prototypes. | In Progress | Alex Johnson | 2023-10-16 / 2023-10-25 | Design reviewed with client on Oct 18.
Development & Implementation | Build the system, code modules, and integrate components. | Not Started | Maria Garcia | 2023-10-26 / 2023-11-15 | Waiting on final design approval.
Testing & QA | Perform unit, integration, and user acceptance testing. | Not Started | Daniel Lee | 2023-11-16 / 2023-11-30 | To be scheduled after development completion.
Deployment & Go-Live | Deploy final system to production environment. | Not Started | Taylor Brown | 2023-12-01 / 2023-12-05 | Rollback plan ready.
Post-Launch Review | Evaluate performance, collect feedback, and document lessons learned. | Not Started | John Doe | 2023-12-06 / 2023-12-15 | To be completed within one week post-launch.
Document Version: 1.0 ¦ Last Updated: October 20, 2023 ¦ Prepared by: Freelancer Project Team