## Worksheet
Process Documentation - Quarterly Project Template
Project Information
Project Name:
Quarter:
Process Overview
Key Processes & Activities
Process ID | Process Name | Description | Owner(s) | Status | Due Date (Quarterly)
P001 | Requirement Gathering | Collect and document all project requirements from stakeholders. | Project Manager | In Progress | Q2 2025 - Mar 31, 2025
P002 | Design Phase | Create detailed technical and UI/UX designs for the system. | Lead Designer & Architect | To Do | Q2 2025 - Apr 15, 2025
P003 | Development Sprint (1) | Implement core features based on initial design. | Development Team | To Do | Q2 2025 - May 15, 2025
P004 | Testing & QA | Perform system and integration testing with bug tracking. | QA Lead & Testers | To Do | Q2 2025 - Jun 30, 2025
P005 | Deployment Preparation | Finalize deployment package and environment setup. | DevOps Engineer | To Do | Q2 2025 - Jun 30, 2025
P006 | User Training & Documentation | Develop training materials and conduct sessions for end-users. | Technical Writer & Trainer | To Do | Q2 2025 - Jul 10, 2025
P007 | Go-Live & Monitoring | Deploy application and monitor performance in production. | Operations Team | To Do | Q2 2025 - Jul 15, 2025
P008 | Post-Implementation Review | Evaluate project success and identify lessons learned. | Project Manager & Stakeholders | To Do | Q2 2025 - Jul 31, 2025
Summary & Metrics (Quarterly)
Planned Tasks: |  |  | Completed:
Metrics | Target | Actual | Benchmark
Project On-Time Delivery Rate (%) | 90%
Defect Density (bugs per 1k lines) | ≤ 1.5
Stakeholder Satisfaction Score (Scale 1–5) | 4.5
Notes & Comments
Enter any additional notes, risks, or concerns here. Include update logs and change requests if applicable.