## Worksheet
Project Timeline - Advanced Template
Phase/Task | Start Date | End Date | Status | Progress (%) | Description
Requirements Gathering | 2024-01-05 | 2024-01-19 | Completed | 100% | Finalized project requirements with stakeholders.
System Design | 2024-01-20 | 2024-02-15 | Completed | 100% | Created UI/UX designs and system architecture.
Core Development | 2024-02-16 | 2024-04-15 | In Progress | 65% | Developing primary application modules and backend services.
Quality Assurance | 2024-04-16 | 2024-05-31 | Delayed | 35% | Testing phase delayed due to requirement changes.
Production Deployment | 2024-06-01 | 2024-06-15 | Delayed | 15% | Deployment scheduled post final testing.
Post-Implementation Review | 2024-06-16 | 2024-07-31 | Delayed | 5% | Final review and documentation after rollout.
Export to ExcelRefresh TimelineAdd New Taskfunction exportToExcel() { const table = document.getElementById('timelineTable'); let html = '<html><head><meta charset="UTF-8"><body>'; html += table.outerHTML; html += '
'; const blob = new Blob([html], { type: 'application/vnd.ms-excel' }); const url = URL.createObjectURL(blob); const a = document.createElement('a'); a.href = url; a.download = 'Project_Timeline_Advanced_Template.xls'; document.body.appendChild(a); a.click(); } function refreshTimeline() { alert('Timeline refreshed successfully.'); } function addNewTask() { const tbody = document.getElementById('timelineData'); const newRow = document.createElement('tr'); newRow.innerHTML = `
|  |  | Delayed | 0% |  | `; tbody.appendChild(newRow); }