## Worksheet
Project Timeline - Analysis View
Phase | Task | Start Date | End Date | Status | Owner(s) | Description
Initiation | Project Charter Approval | 2024-01-05 | 2024-01-15 | In Progress | Jane Doe, John Smith | Finalize project goals and scope.
Analysis | Requirements Gathering | 2024-01-16 | 2024-02-15 | Completed | Alice Johnson, Mark Lee | Capture detailed business and functional requirements.
Analysis | Process Mapping & Workflow Design | 2024-02-16 | 2024-03-15 | In Progress | Alice Johnson, Mark Lee, Sam Chen | Create visual workflow diagrams and process documentation.
Design | System Architecture Review | 2024-03-16 | 2024-04-15 | Pending | Tony Rivera, Priya Patel | Evaluate technical architecture and scalability.
Development | Core Module Development | 2024-04-16 | 2024-06-30 | Pending | Laura Kim, Carlos Mendez, Ben Taylor | Build primary application features and modules.
Testing | Integration Testing | 2024-07-01 | 2024-07-31 | Pending | Rachel Wu, David Kim, Elena Rodriguez | Test interaction between system components.
Deployment | UAT & Final Sign-Off | 2024-08-01 | 2024-08-31 | Pending | Sarah Mitchell, James Wilson, Emma Brown | Conduct user acceptance testing and approval.
Post-Launch | Performance Monitoring & Optimization | 2024-09-01 | 2024-10-31 | Pending | Nathan Reed, Sophia Garcia, Liam White | Monitor system performance and implement improvements.