## Worksheet
Task | Start Date | End Date | Status | Responsible Team/Person
Project Initiation | 2023-10-01 | 2023-10-05 | To Do | Project Manager
Requirement Gathering | 2023-10-06 | 2023-10-15 | In Progress | Business Analysts
Design Phase | 2023-10-16 | 2023-10-30 | In Progress | UI/UX Team
Development (Phase 1) | 2023-10-31 | 2023-11-20 | To Do | Development Team
Testing & QA | 2023-11-21 | 2023-12-05 | To Do | QA Team
User Training & Documentation | 2023-12-06 | 2023-12-15 | To Do | Support Team
Deployment & Go-Live | 2023-12-16 | 2023-12-20 | To Do | IT Operations
Post-Launch Review | 2023-12-21 | 2023-12-31 | To Do | Project Manager