## Worksheet
Project Timeline - Process Documentation
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Initiation | Define Project Scope and Objectives | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe (Project Manager)
Planning | Develop Project Schedule and Resource Plan | 2023-10-16 | 2023-10-31 | Pending | John Smith (Planning Lead)
Execution | Design System Architecture and Components | 2023-11-01 | 2024-01-31 | Pending | Alice Brown (Lead Architect)
Execution | Develop Core Application Modules | 2024-02-01 | 2024-05-31 | Pending | Dev Team - Backend & Frontend
Testing | Conduct Unit, Integration, and System Testing | 2024-06-01 | 2024-07-31 | Pending | QA Team
Deployment | Deploy to Staging and Perform UAT | 2024-08-01 | 2024-08-31 | Pending | DevOps & Business Stakeholders
Closure | Final Review, Documentation, and Project Handover | 2024-09-01 | 2024-09-15 | Pending | Jane Doe (Project Manager)
Project Progress Summary:35% Complete
This document is intended for internal business use. Last updated on October 5, 2023.