## Project Timeline - Client View
Project Timeline - Client View
Phase/Task | Start Date | End Date | Status | Description
Project Kickoff & Planning | 2023-10-01 | 2023-10-15 | Completed | Define project scope, objectives, and stakeholders.
User Interface Design | 2023-10-16 | 2023-11-05 | In Progress | Create wireframes and mockups for client review.
Frontend Development | 2023-11-06 | 2023-12-15 | Pending | Implement responsive design with HTML, CSS, and JavaScript.
Backend Integration | 2023-11-20 | 2024-01-15 | Pending | Develop APIs and database structures.
User Acceptance Testing (UAT) | 2024-01-16 | 2024-01-31 | Pending | Client testing phase to validate functionality.
Final Deployment & Launch | 2024-02-01 | 2024-02-15 | Pending | Go live with full system monitoring.
Project Handover & Documentation | 2024-02-16 | 2024-03-01 | Pending | Provide final documentation and training materials.
Note:This timeline is for client viewing purposes. Actual dates may be adjusted based on feedback and project needs.