## Daily Project Timeline
Daily Project Timeline
Date | Task / Activity | Responsible Team/Person | Status (Completed/In Progress/Pending)
2024-04-01 | Project Kickoff Meeting | Project Manager | In Progress
2024-04-01 | Define Project Scope & Deliverables | Business Analyst, PM | Completed
2024-04-02 | Create Initial Project Plan & Timeline | Project Manager, Team Lead | Pending
2024-04-03 | Identify Key Stakeholders | Business Analyst, PM | Pending
2024-04-05 | Conduct Risk Assessment Workshop | Risk Manager, Project Team | Pending
2024-04-07 | Finalize Project Budget Approval | Finance Team, PM | Pending
2024-04-10 | Begin Design Phase - UI/UX Prototyping | Design Team, Frontend Developer | Pending
2024-04-15 | Develop Core Application Features (MVP) | Backend & Frontend Dev Teams | Pending
2024-04-20 | Internal Testing & QA Cycle 1 | QA Team, Devs | Pending
2024-04-25 | User Acceptance Testing (UAT) | End Users, PM, QA | Pending
2024-04-30 | Finalize Documentation & Training Materials | Technical Writer, Trainer | Pending
Last updated: April 1, 2024 ¦ Project ID: PROJ-DLY-2024-01