## Worksheet
Project Timeline - Dashboard View
Phase/Task | Start Date | End Date | Status | Progress (%)
Project Initiation & Planning | 2024-01-05 | 2024-01-19 | Completed
Requirements Gathering | 2024-01-20 | 2024-01-31 | Completed
Design & Prototyping | 2024-02-01 | 2024-02-15 | In Progress
Development & Implementation | 2024-02-16 | 2024-03-31 | In Progress
Testing & QA | 2024-04-01 | 2024-04-15 | Delayed
User Training & Documentation | 2024-04-16 | 2024-05-15 | Delayed
Deployment & Go-Live | 2024-05-16 | 2024-05-31 | Delayed
Post-Launch Review & Optimization | 2024-06-01 | 2024-06-30 | Delayed
Total Project Duration | 2024-01-05 | 2024-06-30 | Overall Progress: 58%