## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Owner | Dependencies
T001 | Project Initiation & Planning | 2023-10-01 | 2023-10-15 | In Progress | Jane Smith | N/A
T002 | Requirements Gathering | 2023-10-16 | 2023-11-05 | Pending | Mike Johnson | T001
T003 | System Design & Architecture Review | 2023-11-06 | 2023-11-25 | Pending | Sarah Williams | T002
T004 | Development Phase 1 - Core Modules | 2023-11-26 | 2024-01-15 | Pending | David Brown | T003
T005 | Development Phase 2 - Integration & APIs | 2024-01-16 | 2024-03-15 | Pending | Lisa Garcia | T004
T006 | Testing & QA Cycle 1 | 2024-03-16 | 2024-04-30 | Pending | Ryan Davis | T005
T007 | User Acceptance Testing (UAT) | 2024-05-01 | 2024-05-31 | Pending | Nancy Lee | T006
T008 | Final Deployment & Go-Live | 2024-06-01 | 2024-06-15 | Pending | Alex Turner | T007
T009 | Post-Implementation Review & Documentation Finalization | 2024-06-16 | 2024-07-15 | Pending | Jane Smith | T008
Document Version:Data Version 1.2 ¦Last Updated:October 5, 2023
This timeline is part of the Project Timeline - Process Documentation template for tracking project progress and deliverables.