## Worksheet
Project Timeline - Detailed Process Documentation
Phase | Task/Activity | Timeline Details |  |  | Responsible Party | Status
|  | Start Date | End Date | Duration (Days)
Initiation | Project Charter Approval | 2023-10-01 | 2023-10-05 | 5 | Project Manager | In Progress
Planning | Requirements Gathering & Analysis | 2023-10-06 | 2023-10-15 | 10 | Business Analysts, Stakeholders | Completed
Planning | Risk Assessment & Mitigation Planning | 2023-10-16 | 2023-10-20 | 5 | Risk Manager, Project Team | In Progress
Execution | Design Phase – UI/UX Prototyping | 2023-10-21 | 2023-11-05 | 15 | UX Designers, Frontend Developers | Not Started
Execution | Development – Backend Module Implementation | 2023-11-06 | 2023-12-15 | 40 | Backend Developers, DevOps Engineers | Not Started
Execution | Development – Frontend Implementation & Integration Testing | 2023-12-16 | 2024-01-30 | 45 | Frontend Developers, QA Engineers | Not Started
Monitoring & Controlling | Bi-weekly Progress Review Meetings (Agile) | 2023-10-06 | Ongoing | Continuous | Project Manager, Team Leads | In Progress
Monitoring & Controlling | Risk Log Updates and Reviews | 2023-10-06 | Ongoing | Continuous | Risk Manager, Project Team | In Progress
Milestones & Deliverables
Milestone 1: Project Kickoff Complete |  | 2023-10-05 | 2023-10-05 | 1 | Project Manager | Completed
Milestone 2: Design Approval Finalized |  | 2023-11-05 | 2023-11-05 | 1 | UX Lead, Project Manager | In Progress
Milestone 3: Core Module Development Complete |  | 2024-01-30 | 2024-01-30 | 1 | Development Team Lead, QA Manager | Not Started
Project Summary
Total Duration (Planned) |  |  | 120 days (approx. 4 months)
Current Phase |  |  | Planning
Overall Project Status |  |  | On Track (as of 2023-10-10)
Last Updated: October 10, 2023 ¦ Prepared by Project Documentation Team