## Worksheet
Project Timeline - Process Documentation
Phase / Milestone | Start Date | End Date | Status | Responsible Team | Description | Dependencies | Action Items / Notes
Phase 1: Project Initiation | 2024-04-01 | 2024-04-15 | Completed | Project Manager, Stakeholders | Define project scope, objectives, and stakeholders. | N/A | Finalized charter approved by executive board.
| 1.1 Requirements Gathering | 2024-04-01 | 2024-04-08 | Completed | Business Analysts, UX Team | Capture business and user requirements. | Project charter approval | Requirements documented in Confluence.
| 1.2 Stakeholder Identification | 2024-04-08 | 2024-04-15 | Completed | Project Manager, PMO | List all internal and external stakeholders. | Requirements gathering completed | Stakeholder register updated in SharePoint.
Phase 2: Planning & Design | 2024-04-16 | 2024-05-15 | In Progress | Project Manager, Architects, Team Leads | Develop technical design, timelines, and resource plans. | Project initiation complete | Beta design phase starting May 10.
| 2.1 Technical Architecture Design | 2024-04-16 | 2024-05-03 | In Progress | Lead Architect, DevOps Team | Create system architecture diagrams and components. | Requirements finalized | Drafts reviewed May 2.
| 2.2 UI/UX Wireframes & Prototypes | 2024-05-04 | 2024-05-11 | In Progress | UX Designers, Product Owner | Develop interactive prototypes for user testing. | Technical design approved | User feedback session scheduled May 12.
| 2.3 Project Schedule & Risk Assessment | 2024-05-12 | 2024-05-15 | In Progress | Project Manager, Risk Team | Finalize Gantt chart and identify mitigation plans. | All prior tasks completed | Risk register updated weekly.
Phase 3: Development | 2024-05-16 | 2024-07-15 | Delayed | Development Team, QA Leads | Implement and integrate system components. | Design phase completion (delayed) | Budget review required before resumption.
| 3.1 Core Module Development | 2024-05-16 | 2024-06-15 | Delayed | Backend Developers, API Team | Build foundational application modules. | Designs signed off | Development paused due to resource reallocation.
| 3.2 Frontend Implementation | 2024-06-16 | 2024-07-15 | Delayed | Frontend Developers, Designers | Coding user interface components. | Core modules in progress | Waiting for backend endpoints.
| Phase 4: Testing | 2024-07-16 | 2024-08-15 | Delayed | QA Team, DevOps, UAT Leads | Conduct functional, regression & user acceptance testing. | Development phase completion (delayed) | Schedule to begin once development resumes.
|  | Phase 5: Deployment | 2024-08-16 | 2024-09-15 | Delayed | DevOps, IT Operations, Project Manager | Deploy system to production environment. | Testing phase completion (delayed) | Scheduled post-UAT sign-off.
Phase 6: Post-Deployment |  |  | 2024-09-16 | 2024-10-31 | Delayed | Maintenance Team, Support Staff, Project Manager | Monitor system performance and conduct post-mortem. | Deployment completed (delayed) | Training sessions planned for October 10–20.
Notes:
Status Legend: Completed ¦ In Progress ¦ Delayed This timeline is subject to change based on resource availability and stakeholder feedback. Last updated: 2024-04-15