## Worksheet
Phase | Task | Start Date | End Date | Status | Responsible Person
Planning | Define Project Scope | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith
Planning | Develop Timeline & Milestones | 2023-10-06 | 2023-10-10 | Not Started | John Doe
Design | Create System Architecture | 2023-10-11 | 2023-10-18 | Not Started | Alice Johnson
Design | Develop UI Mockups | 2023-10-19 | 2023-10-25 | Not Started | Mike Brown
Development | Build Backend Modules | 2023-10-26 | 2023-11-15 | Not Started | Tina Lee
Development | Develop Frontend Interface | 2023-10-30 | 2023-11-20 | Not Started | Ryan Clark
Testing | Conduct Unit Testing | 2023-11-16 | 2023-11-25 | Not Started | Sophia Garcia
Testing | Perform System Integration Testing | 2023-11-26 | 2023-12-05 | Not Started | Liam Martinez
Deployment | Prepare Production Environment | 2023-12-06 | 2023-12-10 | Not Started | Ella White
Deployment | Release to Production | 2023-12-11 | 2023-12-15 | Not Started | Daniel Harris
Post-Launch | Monitor System Performance | 2023-12-16 | 2024-01-15 | Not Started | Nina Anderson
Post-Launch | Gather Feedback & Make Adjustments | 2024-01-16 | 2024-01-31 | Not Started | Hannah Wilson