## Worksheet
Project Timeline - Large Business Style
Phase | Task Name | Start Date | End Date | Status | Owner | Budget (USD)
Initiation | Project Charter Approval | 2024-01-15 | 2024-01-30 | Completed | Sarah Johnson | $5,000
Planning | Scope Definition & Requirements Gathering | 2024-02-01 | 2024-02-15 | Completed | Daniel Reed | $8,500
| Resource Allocation Plan | 2024-02-16 | 2024-02-28 | Completed | Lisa Chen | $15,000
| Risk Assessment & Mitigation Strategy | 2024-03-01 | 2024-03-15 | In Progress | Michael Torres | $7,800
Execution | Design Phase - UI/UX Prototyping | 2024-03-16 | 2024-04-15 | In Progress | Amanda Foster | $35,000
| Development - Core Modules Implementation | 2024-04-16 | 2024-06-15 | Pending | Tony Williams | $95,000
| Integration Testing with Legacy Systems | 2024-06-16 | 2024-07-15 | Pending | Karen Patel | $38,000
| User Acceptance Testing (UAT) | 2024-07-16 | 2024-08-15 | Pending | Derek Hughes | $25,000
Monitoring & Control | Weekly Progress Review Meetings | 2024-03-16 (Ongoing) | 2024-08-15 | In Progress | Sarah Johnson (PM) | $12,500
| Budget & Timeline Tracking Dashboard Updates | 2024-03-16 (Ongoing) | 2024-08-15 | In Progress | Lisa Chen (Finance) | $9,200
Closeout | Final Project Review & Documentation | 2024-08-16 | 2024-08-31 | Pending | Daniel Reed (QA) | $15,500
© 2024 Large Business Project Management Office. All rights reserved.
Generated on: