## Project Timeline - Manager View
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Priority
T001 | Project Initiation & Planning | 2025-04-01 | 2025-04-15 | In Progress | John Smith, Project Manager | High
T002 | Requirements Gathering Session | 2025-04-16 | 2025-04-30 | Not Started | Alice Johnson, BA Lead | High
M01 | Project Kickoff Meeting (Milestone) | 2025-04-15 | 2025-04-15 | Completed | Team Lead, All Departments | Mandatory
T003 | System Design & Architecture Development | 2025-05-01 | 2025-06-15 | Not Started | Michael Chen, Lead Architect | High
T004 | User Interface Design Phase 1 (Wireframes) | 2025-05-15 | 2025-06-15 | Not Started | Sarah Williams, UX Designer | Medium
M02 | Design Sign-Off (Milestone) | 2025-06-15 | 2025-06-15 | Scheduled | Project Manager, Stakeholders | Mandatory
T005 | Frontend Development (Phase 1) | 2025-06-16 | 2025-08-31 | Not Started | Liam Brown, Frontend Lead | High
T006 | Backend Development (Phase 1) | 2025-07-01 | 2025-09-30 | Not Started | Sophia Lee, Backend Lead | High
T007 | Integration Testing (Internal) | 2025-10-01 | 2025-10-31 | In Progress | Alex Turner, QA Lead | Medium
M03 | Internal Testing Sign-Off (Milestone) | 2025-10-31 | 2025-10-31 | Scheduled | All QA & Dev Teams | Mandatory
T008 | User Acceptance Testing (UAT) | 2025-11-01 | 2025-12-31 | Not Started | Clients & End Users | High
M04 | UAT Sign-Off & Go-Live Approval (Milestone) | 2025-12-31 | 2025-12-31 | Scheduled | CPO, CTO, Project Sponsor | Mandatory
T009 | Production Deployment & Monitoring (Week 1) | 2026-01-01 | 2026-01-31 | Not Started | Tech Ops Team, DevOps Lead | High
T010 | Post-Deployment Review & Lessons Learned Session | 2026-02-01 | 2026-02-15 | Not Started | All Project Team Members | Medium
M05 | Project Closure (Milestone) | 2026-02-15 | 2026-02-15 | Scheduled | CPO, Project Manager, Stakeholders | Mandatory
Project Overview
Project Name:NextGen Platform Launch
Status:On Track
Total Tasks:15 ¦Milestones:5 ¦In Progress Tasks:2
Overall Project Progress
15% Complete