## Project Timeline - Monthly
Project Timeline - Monthly Process Documentation
Month | Week 1 | Week 2 | Week 3 | Week 4 | Status | Notes/Comments
January | Jan 1 - Jan 7 Task A: Project Kickoff Status: In Progress | Jan 8 - Jan 14 Task B: Requirements Gathering Status: Not Started | Jan 15 - Jan 21 Task C: Design Phase Status: Not Started | Jan 22 - Jan 31 Task D: Initial Planning Status: Not Started | In Progress | N/A
February | Feb 1 - Feb 7 Task E: Review Requirements Status: Not Started | Feb 8 - Feb 14 Task F: UI/UX Design Status: Not Started | Feb 15 - Feb 21 Task G: Development Start Status: Not Started | Feb 22 - Feb 28 Task H: Code Review Status: Not Started | In Progress | N/A
March | Mar 1 - Mar 7 Task I: Backend Development Status: Not Started | Mar 8 - Mar 14 Task J: Frontend Development Status: Not Started | Mar 15 - Mar 21 Task K: Integration Testing Status: Not Started | Mar 22 - Mar 31 Task L: UAT Preparation Status: Not Started | In Progress | N/A
April | Apr 1 - Apr 7 Task M: UAT Execution Status: Not Started | Apr 8 - Apr 14 Task N: Bug Fixing Status: Not Started | Apr 15 - Apr 21 Task O: Final Deployment Prep Status: Not Started | Apr 22 - Apr 30 Task P: Production Deployment Status: Not Started | In Progress | N/A
May | May 1 - May 7 Task Q: Post-Deployment Review Status: Not Started | May 8 - May 14 Task R: Documentation Finalization Status: Not Started | May 15 - May 21 Task S: Team Retrospective Status: Not Started | May 22 - May 31 Task T: Project Closure Status: Not Started | In Progress | N/A
*This timeline is a living document. Status updates should be reviewed weekly.